## Sheet1
Besai Hydroelectric Power Project |  |  | STEEL LINER INSTALLATION
WORK SCHEDULE
Sakai Amarta Joint Operation
YEAR | 2000 | [7 empty] | 2001
MONTH | May | June | July | August | September | October | November | December | January | February
Order to Proceed
V
5/19
Design
Design
Material Procurement
Steel Plate Procurement
Shipping
Shipping
Shop Fabrication
Shop Fabrication
Local Transportation
|  |  |  | Local | Transportation
Mobilization
|  | Erection of Base Camp |  | Mobilization
Erection
Erection
Mortar Grouting (by others)
Mortar Grouting by others
Other Civil Remedial Work (by Others)
Other Remedial Work
Surface Repair
Surface Repair
Painting
Painting
Demobilization
Demobilization
Water Filling Test
Test